## 25.09 Summary
ID | Framework | Target SP | Est Dev days | Non-Dev Days | Total DEV days | Dev start date | Dev end date | % Completed
25.09 | KANBAN | 25 | 12 | 1 | 11 | 2025-09-11 | 2025-09-26 | 92.55%
PLANNED | Issues | Story Points | I/S Ratio | Expected SP | To Test | Committed |  |  | Main Assignee | Contract | +Adjustment | =Commitment | Planned | Unplanned | Notes
Angelo Ramirez | 7 | 25 | 3.5714 | 20 | 8 | TRUE |  |  | Angelo Ramirez | 100% | 0 | 100% | 8 | 0
Jose Luis Bautista | 6 | 16 | 2.6667 | 22 | 23 | FALSE |  |  | Jose Luis Bautista | 100% | 0 | 100% | 0
Juan Miguel Santos | 7 | 24 | 3.4286 | 22 | 24 | TRUE |  |  | Juan Miguel Santos | 100% | 0 | 100% | 0
Maria Cristina Dela Cruz | 8 | 26 | 3.25 | 22 | 33 | TRUE |  |  | Maria Cristina Dela Cruz | 100% | 0 | 100% | 0
Patricia Anne Mendoza | 7 | 22 | 3.1429 | 22 | 17 | TRUE |  |  | Patricia Anne Mendoza | 100% | 0 | 100% | 0
TOTAL | 35 | 113 | 3.2119 | 108 | 105 | TRUE
[9 empty] | Leaves | Created Date Time | Start Date Time | End Date Time | Hours | Issue | Leave Type
RELEASED | Issues | Story Points | I/S Ratio | Done % | Tested | Completed |  |  | Angelo Ramirez | 2025-09-10 | 2025-09-11 08:00 | 2025-09-11 17:00 | 8 | AT-234 | Vacation Leave
Angelo Ramirez | 7 | 18 | 2.5714 | 90% | 10 | TRUE
Jose Luis Bautista | 8 | 26 | 3.25 | 118.2% | 20 | TRUE
Juan Miguel Santos | 5 | 15 | 3 | 68.18% | 27 | FALSE
Maria Cristina Dela Cruz | 9 | 27 | 3 | 122.7% | 24 | TRUE
Patricia Anne Mendoza | 4 | 14 | 3.5 | 63.64% | 18 | FALSE
TOTAL | 33 | 100 | 3.0643 | 92.55% | 99 | TRUE

## 25.09 Planned
Issue Type | Key | Summary | Status | Assignee | Capability | Priority | Due Date | Main Assignee | Story Points | Fix Version | Sprint | Peer Tester | Verification Tester | Testing Engineer | Checklist Progress | Checklist Progress % | Epic Link | Labels | Resolution | Resolved | Reporter | Updated | Creator | Created | Removed?
Task | PROJ-1 | Sample issue summary 1 | In Progress | Angelo Ramirez | Backend | High | 2025-09-17 | Angelo Ramirez | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Juan Miguel Santos | Juan Miguel Santos | 2025-04-05 | 75 | EPIC-5 | testing | Fixed | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-03 | FALSE
Story | PROJ-2 | Sample issue summary 2 | To Do | Angelo Ramirez | API | Medium | 2025-09-27 | Angelo Ramirez | 5 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Juan Miguel Santos | 2025-05-05 | 0 | EPIC-5 | ui | Fixed |  | Angelo Ramirez | 2025-09-14 | Jose Luis Bautista | 2025-08-23 | FALSE
Bug | PROJ-3 | Sample issue summary 3 | To Do | Angelo Ramirez | API | High | 2025-09-19 | Angelo Ramirez | 5 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Juan Miguel Santos | Juan Miguel Santos | 2025-03-05 | 75 | EPIC-2 | bugfix | Duplicate | 2025-09-14 | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-28 | FALSE
Task | PROJ-4 | Sample issue summary 4 | To Do | Angelo Ramirez | Backend | Medium | 2025-10-04 | Angelo Ramirez | 1 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Juan Miguel Santos | 2025-02-05 | 100 | EPIC-1 | bugfix | Won't Fix |  | Jose Luis Bautista | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-15 | FALSE
Bug | PROJ-5 | Sample issue summary 5 | To Do | Angelo Ramirez | Backend | High | 2025-09-19 | Angelo Ramirez | 3 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Juan Miguel Santos | Patricia Anne Mendoza | 2025-03-05 | 0 | EPIC-2 | testing | Won't Fix |  | Angelo Ramirez | 2025-09-14 | Juan Miguel Santos | 2025-09-01 | FALSE
Story | PROJ-6 | Sample issue summary 6 | To Do | Angelo Ramirez | Backend | Medium | 2025-10-03 | Angelo Ramirez | 1 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Jose Luis Bautista | Juan Miguel Santos | 2025-04-05 | 50 | EPIC-2 | testing | Fixed |  | Jose Luis Bautista | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-15 | FALSE
Bug | PROJ-7 | Sample issue summary 7 | To Do | Angelo Ramirez | DevOps | High | 2025-09-27 | Angelo Ramirez | 5 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Patricia Anne Mendoza | 2025-03-05 | 100 | EPIC-5 | feature | Unresolved |  | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-03 | FALSE
Story | PROJ-8 | Sample issue summary 8 | Done | Jose Luis Bautista | Frontend | High | 2025-09-30 | Jose Luis Bautista | 3 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Patricia Anne Mendoza | Maria Cristina Dela Cruz | 0/5 | 50 | EPIC-1 | feature | Unresolved |  | Angelo Ramirez | 2025-09-14 | Juan Miguel Santos | 2025-08-30 | FALSE
Task | PROJ-9 | Sample issue summary 9 | Code Review | Jose Luis Bautista | API | Low | 2025-09-22 | Jose Luis Bautista | 2 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | 2025-01-05 | 100 | EPIC-1 | bugfix | Unresolved | 2025-09-14 | Juan Miguel Santos | 2025-09-14 | Patricia Anne Mendoza | 2025-08-24 | FALSE
Story | PROJ-10 | Sample issue summary 10 | To Do | Jose Luis Bautista | Database | Medium | 2025-09-21 | Jose Luis Bautista | 1 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-01-05 | 100 | EPIC-3 | refactor | Unresolved | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Juan Miguel Santos | 2025-08-25 | FALSE
Bug | PROJ-11 | Sample issue summary 11 | In Progress | Jose Luis Bautista | DevOps | Medium | 2025-09-19 | Jose Luis Bautista | 3 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Maria Cristina Dela Cruz | Angelo Ramirez | 0/5 | 0 | EPIC-4 | ui | Duplicate |  | Maria Cristina Dela Cruz | 2025-09-14 | Patricia Anne Mendoza | 2025-09-01 | FALSE
Bug | PROJ-12 | Sample issue summary 12 | Code Review | Jose Luis Bautista | API | High | 2025-09-30 | Jose Luis Bautista | 2 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-03-05 | 0 | EPIC-2 | ui | Unresolved | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Patricia Anne Mendoza | 2025-09-08 | FALSE
Story | PROJ-13 | Sample issue summary 13 | In Progress | Jose Luis Bautista | Backend | High | 2025-09-19 | Jose Luis Bautista | 5 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Maria Cristina Dela Cruz | Juan Miguel Santos | 0/5 | 75 | EPIC-4 | ui | Fixed |  | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-08-22 | FALSE
Bug | PROJ-14 | Sample issue summary 14 | To Do | Juan Miguel Santos | API | Low | 2025-10-03 | Juan Miguel Santos | 2 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | 0/5 | 50 | EPIC-2 | ui | Fixed |  | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-08 | FALSE
Task | PROJ-15 | Sample issue summary 15 | Code Review | Juan Miguel Santos | Database | High | 2025-09-25 | Juan Miguel Santos | 3 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Jose Luis Bautista | 2025-01-05 | 50 | EPIC-1 | refactor | Fixed |  | Juan Miguel Santos | 2025-09-14 | Patricia Anne Mendoza | 2025-08-20 | FALSE
Story | PROJ-16 | Sample issue summary 16 | Code Review | Juan Miguel Santos | Backend | High | 2025-09-26 | Juan Miguel Santos | 3 | v1.4.0 | Sprint 15 | Angelo Ramirez | Jose Luis Bautista | Patricia Anne Mendoza | 2025-04-05 | 100 | EPIC-4 | refactor | Duplicate | 2025-09-14 | Juan Miguel Santos | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-24 | FALSE
Story | PROJ-17 | Sample issue summary 17 | Done | Juan Miguel Santos | Database | High | 2025-09-27 | Juan Miguel Santos | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Jose Luis Bautista | 2025-03-05 | 75 | EPIC-1 | testing | Duplicate |  | Maria Cristina Dela Cruz | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-06 | FALSE
Task | PROJ-18 | Sample issue summary 18 | Done | Juan Miguel Santos | Frontend | High | 2025-09-17 | Juan Miguel Santos | 4 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Maria Cristina Dela Cruz | Jose Luis Bautista | 0/5 | 0 | EPIC-5 | bugfix | Fixed |  | Angelo Ramirez | 2025-09-14 | Juan Miguel Santos | 2025-08-24 | FALSE
Bug | PROJ-19 | Sample issue summary 19 | To Do | Juan Miguel Santos | Backend | High | 2025-10-02 | Juan Miguel Santos | 2 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Angelo Ramirez | 2025-03-05 | 100 | EPIC-2 | refactor | Duplicate | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-15 | FALSE
Task | PROJ-20 | Sample issue summary 20 | Done | Juan Miguel Santos | Database | Low | 2025-09-16 | Juan Miguel Santos | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Patricia Anne Mendoza | 2025-02-05 | 50 | EPIC-1 | testing | Fixed |  | Patricia Anne Mendoza | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-09 | FALSE
Task | PROJ-21 | Sample issue summary 21 | Code Review | Maria Cristina Dela Cruz | Backend | Low | 2025-09-27 | Maria Cristina Dela Cruz | 2 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Jose Luis Bautista | 2025-02-05 | 100 | EPIC-4 | feature | Won't Fix | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-26 | FALSE
Bug | PROJ-22 | Sample issue summary 22 | Code Review | Maria Cristina Dela Cruz | Backend | Medium | 2025-10-02 | Maria Cristina Dela Cruz | 5 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Jose Luis Bautista | Juan Miguel Santos | 2025-04-05 | 50 | EPIC-3 | testing | Won't Fix | 2025-09-14 | Angelo Ramirez | 2025-09-14 | Jose Luis Bautista | 2025-08-23 | FALSE
Bug | PROJ-23 | Sample issue summary 23 | Code Review | Maria Cristina Dela Cruz | Backend | Low | 2025-09-18 | Maria Cristina Dela Cruz | 5 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Juan Miguel Santos | Juan Miguel Santos | 0/5 | 25 | EPIC-3 | refactor | Fixed |  | Patricia Anne Mendoza | 2025-09-14 | Patricia Anne Mendoza | 2025-08-25 | FALSE
Task | PROJ-24 | Sample issue summary 24 | In Progress | Maria Cristina Dela Cruz | DevOps | Low | 2025-09-18 | Maria Cristina Dela Cruz | 2 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Angelo Ramirez | Jose Luis Bautista | 2025-03-05 | 75 | EPIC-4 | bugfix | Duplicate | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Juan Miguel Santos | 2025-09-07 | FALSE
Task | PROJ-25 | Sample issue summary 25 | Done | Maria Cristina Dela Cruz | DevOps | High | 2025-10-04 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Angelo Ramirez | Patricia Anne Mendoza | 2025-03-05 | 25 | EPIC-2 | bugfix | Fixed | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-04 | FALSE
Task | PROJ-26 | Sample issue summary 26 | Code Review | Maria Cristina Dela Cruz | API | Low | 2025-10-04 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Juan Miguel Santos | Patricia Anne Mendoza | 2025-02-05 | 25 | EPIC-4 | feature | Won't Fix | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Angelo Ramirez | 2025-08-18 | FALSE
Bug | PROJ-27 | Sample issue summary 27 | Code Review | Maria Cristina Dela Cruz | API | High | 2025-09-23 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Patricia Anne Mendoza | Patricia Anne Mendoza | 0/5 | 50 | EPIC-1 | refactor | Duplicate | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-08 | FALSE
Story | PROJ-28 | Sample issue summary 28 | Done | Maria Cristina Dela Cruz | Database | Medium | 2025-09-21 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Angelo Ramirez | Jose Luis Bautista | Patricia Anne Mendoza | 0/5 | 0 | EPIC-1 | feature | Duplicate | 2025-09-14 | Juan Miguel Santos | 2025-09-14 | Angelo Ramirez | 2025-09-06 | FALSE
Task | PROJ-29 | Sample issue summary 29 | In Progress | Patricia Anne Mendoza | Frontend | Low | 2025-09-28 | Patricia Anne Mendoza | 3 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | 2025-02-05 | 25 | EPIC-4 | refactor | Duplicate |  | Juan Miguel Santos | 2025-09-14 | Juan Miguel Santos | 2025-08-19 | FALSE
Bug | PROJ-30 | Sample issue summary 30 | In Progress | Patricia Anne Mendoza | Frontend | High | 2025-09-27 | Patricia Anne Mendoza | 2 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | 2025-04-05 | 50 | EPIC-1 | bugfix | Unresolved | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Jose Luis Bautista | 2025-09-04 | FALSE
Task | PROJ-31 | Sample issue summary 31 | To Do | Patricia Anne Mendoza | DevOps | Medium | 2025-09-25 | Patricia Anne Mendoza | 1 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Jose Luis Bautista | Juan Miguel Santos | 2025-03-05 | 25 | EPIC-2 | bugfix | Unresolved |  | Patricia Anne Mendoza | 2025-09-14 | Patricia Anne Mendoza | 2025-08-27 | FALSE
Bug | PROJ-32 | Sample issue summary 32 | To Do | Patricia Anne Mendoza | API | Low | 2025-09-19 | Patricia Anne Mendoza | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Jose Luis Bautista | 2025-04-05 | 50 | EPIC-5 | refactor | Duplicate | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Patricia Anne Mendoza | 2025-08-23 | FALSE
Story | PROJ-33 | Sample issue summary 33 | Code Review | Patricia Anne Mendoza | Database | Low | 2025-09-19 | Patricia Anne Mendoza | 3 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-05-05 | 25 | EPIC-3 | testing | Duplicate |  | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-16 | FALSE
Story | PROJ-34 | Sample issue summary 34 | To Do | Patricia Anne Mendoza | Database | Medium | 2025-09-30 | Patricia Anne Mendoza | 3 | v1.4.0 | Sprint 15 | Angelo Ramirez | Angelo Ramirez | Jose Luis Bautista | 2025-05-05 | 50 | EPIC-2 | ui | Won't Fix | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Jose Luis Bautista | 2025-09-01 | FALSE
Bug | PROJ-35 | Sample issue summary 35 | Done | Patricia Anne Mendoza | Database | Medium | 2025-09-20 | Patricia Anne Mendoza | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Jose Luis Bautista | Jose Luis Bautista | 2025-01-05 | 25 | EPIC-2 | ui | Duplicate | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-07 | FALSE

## 25.09 Released
Issue Type | Key | Summary | Status | Assignee | Capability | Priority | Due Date | Main Assignee | Story Points | Fix Version | Sprint | Peer Tester | Verification Tester | Testing Engineer | Checklist Progress | Checklist Progress % | Epic Link | Labels | Resolution | Resolved | Reporter | Updated | Creator | Created | Added?
Task | PROJ-1 | Sample issue summary 1 | In Progress | Angelo Ramirez | Backend | High | 2025-09-17 | Angelo Ramirez | 4 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Juan Miguel Santos | Juan Miguel Santos | 2025-04-05 | 75 | EPIC-5 | testing | Fixed | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-03 | FALSE
Story | PROJ-2 | Sample issue summary 2 | To Do | Angelo Ramirez | API | Medium | 2025-09-27 | Angelo Ramirez | 3 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Juan Miguel Santos | 2025-05-05 | 0 | EPIC-5 | ui | Fixed |  | Angelo Ramirez | 2025-09-14 | Jose Luis Bautista | 2025-08-23 | FALSE
Bug | PROJ-3 | Sample issue summary 3 | To Do | Angelo Ramirez | API | High | 2025-09-19 | Angelo Ramirez | 1 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Juan Miguel Santos | Juan Miguel Santos | 2025-03-05 | 75 | EPIC-2 | bugfix | Duplicate | 2025-09-14 | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-28 | FALSE
Task | PROJ-4 | Sample issue summary 4 | To Do | Angelo Ramirez | Backend | Medium | 2025-10-04 | Angelo Ramirez | 2 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Juan Miguel Santos | 2025-02-05 | 100 | EPIC-1 | bugfix | Won't Fix |  | Jose Luis Bautista | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-15 | FALSE
Bug | PROJ-5 | Sample issue summary 5 | To Do | Angelo Ramirez | Backend | High | 2025-09-19 | Angelo Ramirez | 4 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Juan Miguel Santos | Patricia Anne Mendoza | 2025-03-05 | 0 | EPIC-2 | testing | Won't Fix |  | Angelo Ramirez | 2025-09-14 | Juan Miguel Santos | 2025-09-01 | FALSE
Story | PROJ-6 | Sample issue summary 6 | To Do | Angelo Ramirez | Backend | Medium | 2025-10-03 | Angelo Ramirez | 2 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Jose Luis Bautista | Juan Miguel Santos | 2025-04-05 | 50 | EPIC-2 | testing | Fixed |  | Jose Luis Bautista | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-15 | FALSE
Bug | PROJ-7 | Sample issue summary 7 | To Do | Angelo Ramirez | DevOps | High | 2025-09-27 | Angelo Ramirez | 2 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Patricia Anne Mendoza | 2025-03-05 | 100 | EPIC-5 | feature | Unresolved |  | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-03 | FALSE
Story | PROJ-8 | Sample issue summary 8 | Done | Jose Luis Bautista | Frontend | High | 2025-09-30 | Jose Luis Bautista | 4 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Patricia Anne Mendoza | Maria Cristina Dela Cruz | 0/5 | 50 | EPIC-1 | feature | Unresolved |  | Angelo Ramirez | 2025-09-14 | Juan Miguel Santos | 2025-08-30 | FALSE
Task | PROJ-9 | Sample issue summary 9 | Code Review | Jose Luis Bautista | API | Low | 2025-09-22 | Jose Luis Bautista | 2 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | 2025-01-05 | 100 | EPIC-1 | bugfix | Unresolved | 2025-09-14 | Juan Miguel Santos | 2025-09-14 | Patricia Anne Mendoza | 2025-08-24 | FALSE
Story | PROJ-10 | Sample issue summary 10 | To Do | Jose Luis Bautista | Database | Medium | 2025-09-21 | Jose Luis Bautista | 1 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-01-05 | 100 | EPIC-3 | refactor | Unresolved | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Juan Miguel Santos | 2025-08-25 | FALSE
Bug | PROJ-11 | Sample issue summary 11 | In Progress | Jose Luis Bautista | DevOps | Medium | 2025-09-19 | Jose Luis Bautista | 3 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Maria Cristina Dela Cruz | Angelo Ramirez | 0/5 | 0 | EPIC-4 | ui | Duplicate |  | Maria Cristina Dela Cruz | 2025-09-14 | Patricia Anne Mendoza | 2025-09-01 | FALSE
Bug | PROJ-12 | Sample issue summary 12 | Code Review | Jose Luis Bautista | API | High | 2025-09-30 | Jose Luis Bautista | 2 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-03-05 | 0 | EPIC-2 | ui | Unresolved | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Patricia Anne Mendoza | 2025-09-08 | FALSE
Story | PROJ-13 | Sample issue summary 13 | In Progress | Jose Luis Bautista | Backend | High | 2025-09-19 | Jose Luis Bautista | 5 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Maria Cristina Dela Cruz | Juan Miguel Santos | 0/5 | 75 | EPIC-4 | ui | Fixed |  | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-08-22 | FALSE
Story | PROJ-16 | Sample issue summary 16 | Code Review | Juan Miguel Santos | Backend | High | 2025-09-26 | Juan Miguel Santos | 3 | v1.4.0 | Sprint 15 | Angelo Ramirez | Jose Luis Bautista | Patricia Anne Mendoza | 2025-04-05 | 100 | EPIC-4 | refactor | Duplicate | 2025-09-14 | Juan Miguel Santos | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-24 | FALSE
Story | PROJ-17 | Sample issue summary 17 | Done | Juan Miguel Santos | Database | High | 2025-09-27 | Juan Miguel Santos | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Jose Luis Bautista | 2025-03-05 | 75 | EPIC-1 | testing | Duplicate |  | Maria Cristina Dela Cruz | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-06 | FALSE
Task | PROJ-18 | Sample issue summary 18 | Done | Juan Miguel Santos | Frontend | High | 2025-09-17 | Juan Miguel Santos | 4 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Maria Cristina Dela Cruz | Jose Luis Bautista | 0/5 | 0 | EPIC-5 | bugfix | Fixed |  | Angelo Ramirez | 2025-09-14 | Juan Miguel Santos | 2025-08-24 | FALSE
Bug | PROJ-19 | Sample issue summary 19 | To Do | Juan Miguel Santos | Backend | High | 2025-10-02 | Juan Miguel Santos | 2 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Angelo Ramirez | 2025-03-05 | 100 | EPIC-2 | refactor | Duplicate | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-15 | FALSE
Task | PROJ-20 | Sample issue summary 20 | Done | Juan Miguel Santos | Database | Low | 2025-09-16 | Juan Miguel Santos | 1 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Patricia Anne Mendoza | 2025-02-05 | 50 | EPIC-1 | testing | Fixed |  | Patricia Anne Mendoza | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-09 | FALSE
Task | PROJ-21 | Sample issue summary 21 | Code Review | Maria Cristina Dela Cruz | Backend | Low | 2025-09-27 | Maria Cristina Dela Cruz | 2 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Patricia Anne Mendoza | Jose Luis Bautista | 2025-02-05 | 100 | EPIC-4 | feature | Won't Fix | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-26 | FALSE
Bug | PROJ-22 | Sample issue summary 22 | Code Review | Maria Cristina Dela Cruz | Backend | Medium | 2025-10-02 | Maria Cristina Dela Cruz | 1 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Jose Luis Bautista | Juan Miguel Santos | 2025-04-05 | 50 | EPIC-3 | testing | Won't Fix | 2025-09-14 | Angelo Ramirez | 2025-09-14 | Jose Luis Bautista | 2025-08-23 | FALSE
Bug | PROJ-23 | Sample issue summary 23 | Code Review | Maria Cristina Dela Cruz | Backend | Low | 2025-09-18 | Maria Cristina Dela Cruz | 5 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Juan Miguel Santos | Juan Miguel Santos | 0/5 | 25 | EPIC-3 | refactor | Fixed |  | Patricia Anne Mendoza | 2025-09-14 | Patricia Anne Mendoza | 2025-08-25 | FALSE
Task | PROJ-24 | Sample issue summary 24 | In Progress | Maria Cristina Dela Cruz | DevOps | Low | 2025-09-18 | Maria Cristina Dela Cruz | 2 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Angelo Ramirez | Jose Luis Bautista | 2025-03-05 | 75 | EPIC-4 | bugfix | Duplicate | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-14 | Juan Miguel Santos | 2025-09-07 | FALSE
Task | PROJ-25 | Sample issue summary 25 | Done | Maria Cristina Dela Cruz | DevOps | High | 2025-10-04 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Angelo Ramirez | Patricia Anne Mendoza | 2025-03-05 | 25 | EPIC-2 | bugfix | Fixed | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Maria Cristina Dela Cruz | 2025-09-04 | FALSE
Task | PROJ-26 | Sample issue summary 26 | Code Review | Maria Cristina Dela Cruz | API | Low | 2025-10-04 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Juan Miguel Santos | Patricia Anne Mendoza | 2025-02-05 | 25 | EPIC-4 | feature | Won't Fix | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Angelo Ramirez | 2025-08-18 | FALSE
Bug | PROJ-27 | Sample issue summary 27 | Code Review | Maria Cristina Dela Cruz | API | High | 2025-09-23 | Maria Cristina Dela Cruz | 4 | v1.4.0 | Sprint 15 | Juan Miguel Santos | Patricia Anne Mendoza | Patricia Anne Mendoza | 0/5 | 50 | EPIC-1 | refactor | Duplicate | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-08 | FALSE
Story | PROJ-28 | Sample issue summary 28 | Done | Maria Cristina Dela Cruz | Database | Medium | 2025-09-21 | Maria Cristina Dela Cruz | 3 | v1.4.0 | Sprint 15 | Angelo Ramirez | Jose Luis Bautista | Patricia Anne Mendoza | 0/5 | 0 | EPIC-1 | feature | Duplicate | 2025-09-14 | Juan Miguel Santos | 2025-09-14 | Angelo Ramirez | 2025-09-06 | FALSE
Task | PROJ-31 | Sample issue summary 31 | To Do | Patricia Anne Mendoza | DevOps | Medium | 2025-09-25 | Patricia Anne Mendoza | 1 | v1.4.0 | Sprint 15 | Jose Luis Bautista | Jose Luis Bautista | Juan Miguel Santos | 2025-03-05 | 25 | EPIC-2 | bugfix | Unresolved |  | Patricia Anne Mendoza | 2025-09-14 | Patricia Anne Mendoza | 2025-08-27 | FALSE
Bug | PROJ-32 | Sample issue summary 32 | To Do | Patricia Anne Mendoza | API | Low | 2025-09-19 | Patricia Anne Mendoza | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Jose Luis Bautista | 2025-04-05 | 50 | EPIC-5 | refactor | Duplicate | 2025-09-14 | Patricia Anne Mendoza | 2025-09-14 | Patricia Anne Mendoza | 2025-08-23 | FALSE
Story | PROJ-33 | Sample issue summary 33 | Code Review | Patricia Anne Mendoza | Database | Low | 2025-09-19 | Patricia Anne Mendoza | 3 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-05-05 | 25 | EPIC-3 | testing | Duplicate |  | Angelo Ramirez | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-16 | FALSE
Bug | PROJ-35 | Sample issue summary 35 | Done | Patricia Anne Mendoza | Database | Medium | 2025-09-20 | Patricia Anne Mendoza | 5 | v1.4.0 | Sprint 15 | Maria Cristina Dela Cruz | Jose Luis Bautista | Jose Luis Bautista | 2025-01-05 | 25 | EPIC-2 | ui | Duplicate | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-07 | FALSE
Story | PROJ-36 | Newly added issue 36 | In Progress | Maria Cristina Dela Cruz | API | High | 2025-09-29 | Maria Cristina Dela Cruz | 4 | v1.4.0 | Sprint 15 | Angelo Ramirez | Angelo Ramirez | Juan Miguel Santos | 2025-03-05 | 25 | EPIC-1 | feature | Won't Fix | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Patricia Anne Mendoza | 2025-09-02 | FALSE
Story | PROJ-37 | Newly added issue 37 | Done | Jose Luis Bautista | Database | Medium | 2025-09-19 | Jose Luis Bautista | 4 | v1.4.0 | Sprint 15 | Angelo Ramirez | Angelo Ramirez | Juan Miguel Santos | 2025-01-05 | 75 | EPIC-5 | testing | Fixed |  | Juan Miguel Santos | 2025-09-14 | Maria Cristina Dela Cruz | 2025-08-18 | FALSE
Story | PROJ-38 | Newly added issue 38 | To Do | Jose Luis Bautista | DevOps | Medium | 2025-09-26 | Jose Luis Bautista | 5 | v1.4.0 | Sprint 15 | Patricia Anne Mendoza | Maria Cristina Dela Cruz | Juan Miguel Santos | 2025-02-05 | 100 | EPIC-4 | refactor | Won't Fix | 2025-09-14 | Jose Luis Bautista | 2025-09-14 | Angelo Ramirez | 2025-09-08 | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE